## Product Backlog
ID | Name | As a/an | I want to… | so that… | Priority | Story points | Status
1 | Register | User | Be able to create an account | I can login in | 1 | 8
2 | Login | User | Be able to login | I can search for people | 1 | 5
3 | Update profile | User | Be able to update my profile picture, information and passions | people can find me
4 | Delete account | User | Be able to delete the account | I can remove myself from searches
5 | Search and show | User | Be able to search the search for other people with certain passions | I can send a Connection request | 2 | 15
6 | Narrow search | User | Be able to narrow a search by criteria | I can find certain people(closer, far away..) | 2 | 3
7 | Check details | User | Be able to select a person from result | I can see the details about it | 2 | 1
8 | Send connection request | User | Be able to send a connection request | I can talk with that person | 3 | 2
9 | Accept & Matching | User | Be able to accept connection requests | I can add a person from connection list | 3 | 6
10 | Remove/decline request | User | Be able to remove/decline connection request | I can remove/decline a person from connection list | 3 | 1
11 | Report user | User | Be able to report another user | I can remove spammer and annoying people
12 | Send message | User | Be able to message one or more people | I can interact with them | 4 | 10
13 | Answer message | User | Be able to answer to messages | We can have a dialog | 4 | 4
14 | Create group | User | Be able to create a group | I can message multiple people at once
15 | Delete group | User | Be able to delete a group | I can remove a discution from list
16 | Add person to group | User | Be able to add a person to group | they can see the entire discution
17 | Remove person from group | User | Be able to remove a person from a group | they don't see the discution anymore
18 | Search person | User | Be able to search for a person in chat/group chat | I can private message it
19 | Book assistance | User | Book an advisor | I can book an advisor and ask for help | 5 | 12
20 | Block users from app | Administrator | Be able to block users from accessing the service (ban ip and account) | I can remove fraud
21 | Warn users from app | Adminsitartor | Be able to warn users if they make mistakes | I can maintain a balanced community
22 | Add premium service | Administrator | Be able to add a premium service | I can get more income
23 | Remove premium service | Administrator | be able to remove a premium service | I can protect the users from buying a non-existing service
24 | Premium service price | Administrator | Be able to change the price of the premium service | I can create discount
25 | Make users administrators | Administrator | Be able to allow another user to become an administrator | I can hire people that can use the app.
26 | Remove users rights | Administrator | Be able to drank an administrator to become a user. | I can fire people.
Add here more
Delete messages

## Details
ID | How to | Acceptance criteria
1 | The user will see a register button on the screen. After he presses the button he will get to a new screen where he can input his information (name, username, password, address, passios, phone no., e-mail). After he presses register he will have an account. | information is the right format, username is not taken, e-mail not used
2 | The user will see two boxes where he can input his username/email and password. After he presses the login button the user is logged in into the app. | username/email exists, password is correct for that username
3 | While he is logged in the user can press the My Profile button which will lead to a page with that user's information. He can edit every cell (except username) and he can press the save button to save the changes | inormation is the right format
4 | On the bottom of the profile page is the delete button. The user will be able to press the button and delete the account. As a verification method he will be asked to enter his password | password is correct
5 | Pressing the Search for connection button will allow the user to seach for people with certain passions.
6 | Selecting certain passions or selecting a distance will narrrow the search to a certain area. (more fields can be added: age, gender )
7 | Clicking on a person from the search result will allow the user to see all the information about the user and the Add Connection button
8 | Pressing the add connection button will sent a connection request
9 | When pressented with connection requests on the top of the screen the user can interact with it (see profile, accept, decline)
10 | By going to the chat and selecting a connection the user can go to their profile. On the profile the user will see remove connection as a button. Pressing it will remove the connection.
11 | On the bottom of every profile page is the report user button. | the users are connected
12 | By sliding from the left side of the screen the user will reveal the chat. Selecting a connection or a group will allow the user to send messages. | at least one connection exists
13 | By sliding from the left side of the screen the user will reveal the chat.The connection/group with new messages changed color. Selecting a connection or a group will allow the user to answer to messages.
14 | In the chat the user can press the Create group button. In there he will pressed with Add connection to group, Remove connection from group, Delete group buttons. | at least one connection exists
15 | By going into the chat the user can select a group.If he presses the details button he will see a list will all connections from the group and the Add/Remove connection and delete buttons. Pressing the delete group button will remove the group. | Group exists
16 | Selecting add connection will show a list will all connections. The user will be able to select a connection and add it to the group. | Group exists
17 | Selecting remvoe connection will show a list will all connections from that group. The user will be able to select a connection and remove it to the group. | Group exists
18 | Selecting the search field on the top of a group chat will allow the user to seach and interact just with one connection from that group. | Group exists
19 | In the store the user can purchase online help. Purchasing the package will allow the user to message a 24/7 help service. | Premium pachages are available
20
21
22
23
24
25
26

## Tasks
Tasks
Sprint 1 | story | points | tasks
| Register |  | create database, register interface, connections, querries | Ionut | Report Writing, Candidate Class Diagram - Richard
| Login |  | login interface, connections, querries | Ionut | Leo - Design Class Diagram, Technology Report,
| Start Search |  | search algorythm, retrieve info order, compare data, | Alex

## Team Roles
1st
Scrum Master | Richard
Client | Ionut
Programmer | Leo
2nd programmer | Alex
Stand up meeting agreement
11:00 | when not at school
8:30 | when at school
summarizing previous results
deciding on following steps
checking milestones
Development Environment
Have all software on all the laptops
We use Visual Studio for coding in C#
Test phone is a Windows Phone running on Windows 8