## Munka1
ID | Date | Description | Probability | Effect | Ranking | Mitigation | How to handle
6 |  | Financial Crisis | 7 | 9 | 63 | Financial reservers | lower costs and expenses
4 |  | Spams | 8 | 5 | 40 | Block functionality and anti-bot | Use Block
3 |  | Database query error | 3 | 9 | 27 | Back-up databases | Switch to back
2 |  | System is hacked | 2 | 10 | 20 | Regular security upgrades | Turn off servers
5 |  | Power shutdown | 2 | 10 | 20 | Back up Generator | Use Back Up Generator
1 |  | Miscalculating target group | 10 | 1 | 10 | Target group survey | Switch platforms
7 |  | Forward compatibility | 1 | 10 | 10 | Examine possible switch to other platforms | Switch platforms
ID | Date | Description | Probability | Effect | Ranking | Mitigation | How to handle
2 |  | late from meetings | 6 | 6 | 36 | Set up a meeting time fittig to everyone | Fines for being late
6 |  | Attendance | 4 | 9 | 36 | Require regular attendance | Fire person
5 |  | lack of communication | 4 | 8 | 32 | decide on communication platform | find better ways to communicate
3 |  | lack of skills | 3 | 10 | 30 | Check skills | Tutorials and practices
4 |  | quitting | 3 | 10 | 30 | check availability | Find new person
1 |  | sickness | 7 | 4 | 28 | Dress accordingly to weather | Medicines